## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File | Comment1
3654682 | 68514 | ATM Project | 1 | ATM_1-1 | 293418 | Bug | 92941 | Manual Scripted | 64063 | 1.0 | System dispenses the incorrect amount of cash other than the selected amount. | Function Being Tested:System performing legitimate withdrawal transaction Initial State of the System:System is on and the screen is displaying the amounts to be withdrawn Input:Choosing the amount to be dispensed not greater than the balance of the account Expected Output:System dispensing the correct amount of cash to be withdrawn, prints the receipt accordingly by recording the transaction in the log. Actual Output:System dispenses the wrong amount of cash which is either greater than or less than the selected value to be withdrawn. It prints the receipt according to the wrong amount that has been dispensed and the transaction is recorded in the logs. | 3 | Resolved | 2 | High |  |  |  |  | 320198 | LAB1-17 | 320198 | LAB1-17 | Jan. 27, 2022 12:28 | Feb. 02, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:06 | 0 | 0 | Jan. 30, 2022 13:06 LAB1-17 Defect does not exist in version 1.1
3654693 | 68514 | ATM Project | 2 | ATM_1-2 | 293418 | Bug | 92941 | Manual Scripted | 64063 | 1.0 | System performing incorrect deposit transaction | Function Being Tested :Testing the system for legitimate deposit transaction Initial State of the System :System requests the customer to insert a envelope Input :Customer inserting the envolope Expected Output :System accepts the envelope properly and deposits the correct amount into the account selected. The receipt gets printed by the system with the updated balance and a correct log is recorded. Actual Output : System accepts the envelope and deposits the incorrect amount of cash into the selected account and generates the receipt. | 2 | In Progress | 3 | Normal |  |  |  |  | 320199 | SATYA RELLU | 320198 | LAB1-17 | Jan. 27, 2022 12:44 | Feb. 02, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:08 | 0 | 0 | Jan. 30, 2022 13:09 LAB1-17 Defect still exists in version 1.1
3654701 | 68514 | ATM Project | 3 | ATM_1-3 | 293418 | Bug | 92941 | Manual Scripted | 64063 | 1.0 | System transfers the incorrect amount of cash between the accounts | Function Being Tested :Testing the system for legitimate transfer transaction Initial State of the System :System requests the customer to enter the legitimate amount to be transferred (dollar type) Input :Customer enters the dollar amount Expected Output :System transfers the correct amount to the selected account and generates the receipt showing the correct updated balance of the account. The correct transaction has to be recorded in the log. Actual Output : System transfers the incorrect dollar amount to the selected account and the respective incorrect updated balance is shown in the receipt generated. The respective incorrect transaction is recorded in the log. | 3 | Resolved | 3 | Normal |  |  |  |  | 320201 | KARTHIK KUMAR REDDY GANGIREDDY | 320198 | LAB1-17 | Jan. 27, 2022 12:56 | Feb. 03, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:08 | 0 | 0 | Jan. 30, 2022 13:12 LAB1-17 Defect does not exist in version 1.1
3654719 | 68514 | ATM Project | 4 | ATM_1-4 | 293418 | Bug | 92941 | Manual Scripted | 64063 | 1.0 | System displaying unavailable accounts types for all transaction types. | Function Being Tested : System asking the customer to choose the account from the selected transaction type. Initial State of the System : To choose the transaction types. Input : Selecting the inquiry transaction type. Expected Output : System displaying a menu of valid account types available. Actual Output : System displaying unavailable account types. | 2 | In Progress | 3 | Normal |  |  |  |  | 320200 | Chandrahas Reddy Pola | 320198 | LAB1-17 | Jan. 27, 2022 13:16 | Feb. 03, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:09 | 0 | 0 | Jan. 30, 2022 13:13 LAB1-17 Defect still exists in version 1.1
3654761 | 68514 | ATM Project | 5 | ATM_1-5 | 293418 | Bug | 92941 | Manual Scripted | 64063 | 1.0 | System asks to re-enter the correct pin even after entering the correct pin after the invalid pin entry in first attempt. | Function Being Tested : Checking for the correct re-entry of the pin on the second try after an invalid pin attempt. Initial State of the System : Request for the re-entry of the pin is displayed. Input : Entering the incorrect pin in the first try and correct pin in the second attempt. Expected Output : Transaction is completed successfully and a menu of transaction types gets displayed. Actual Output : System asks to re-enter the correct pin again. | 2 | In Progress | 3 | Normal |  |  |  |  | 320198 | LAB1-17 | 320198 | LAB1-17 | Jan. 27, 2022 13:42 | Feb. 02, 2022 | 320198 | LAB1-17 | Jan. 30, 2022 13:13 | 0 | 0 | Jan. 30, 2022 13:13 LAB1-17 Defect still exists in version 1.1
3654831 | 68514 | ATM Project | 6 | ATM_1-6 | 293418 | Bug | 92944 | Exploratory | 64063 | 1.0 | System gets frozen when inserted a wrong card, numbered 3. | Function Being Tested: System Initial State of the System: The system requests the customer to enter the card number. Input: Customer inserting the card numbered 3. Expected Output: The system asks for the pin number related to the card number and should eject the card due to an unregistered card number. Actual Output: The system is ejecting the card for all the other card numbers when a random pin is entered except for card number 3. Instead, the system is getting frozen in this specific case. | 3 | Resolved | 3 | Normal |  |  |  |  | 320198 | LAB1-17 | 320198 | LAB1-17 | Jan. 27, 2022 15:35 | Feb. 03, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:10 | 0 | 0 | Jan. 30, 2022 13:14 LAB1-17 Defect does not exist in version 1.1
3654850 | 68514 | ATM Project | 7 | ATM_1-7 | 293418 | Bug | 92944 | Exploratory | 64063 | 1.0 | Retained Card is still accessible for transactions after 3 failed pin attempts. | Function Being Tested: Retention of the inserted card after 3 incorrect PIN attempts. Initial State of the System: The system asks the customer for the correct PIN related to the inserted card. Input: 3 incorrect PIN's are entered. Expected Output: Following the 3 failed PIN attempts, the inserted card is retained and the customer is asked to contact the bank. Actual Output: After 3 failed PIN attempts, the system retains the card. When the same card is reinserted again, the system allows for PIN attempts and if the correct PIN is entered then the system logs in. | 2 | In Progress | 3 | Normal |  |  |  |  | 320198 | LAB1-17 | 320198 | LAB1-17 | Jan. 27, 2022 15:54 | Feb. 03, 2022 | 320198 | LAB1-17 | Jan. 30, 2022 13:17 | 0 | 0 | Jan. 30, 2022 13:17 LAB1-17 Defect still exists in version 1.1
3654866 | 68514 | ATM Project | 8 | ATM_1-8 | 293418 | Bug | 92944 | Exploratory | 64063 | 1.0 | System prints the receipt with incorrect card number | Function Being Tested: System performs the selected transaction of the accounts that are linked to the card and generates the receipt. Initial State of the System: System asks the customer to choose the account type. Input:Customer selects the account type. Expected Output: System performs the selected transaction type and generates the receipts with the correct card number. Actual Output: System performs the selected transaction and generates the incorrect card number on the receipt. | 2 | In Progress | 4 | Low |  |  |  |  | 320200 | Chandrahas Reddy Pola | 320198 | LAB1-17 | Jan. 27, 2022 16:18 | Feb. 03, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:15 | 0 | 0 | Jan. 30, 2022 13:18 LAB1-17 Defect still exists in version 1.1
3654894 | 68514 | ATM Project | 9 | ATM_1-9 | 293418 | Bug | 92944 | Exploratory | 64063 | 1.0 | Invalid prompt | Function Being Tested: Systems response for given invalid inputs. Initial State of the System: Displaying the available options. Input: Giving an invalid input. Expected Output: Prompts a message to "Select a valid input" Actual Output Prompts a message with "Invalid amount" | 3 | Resolved | 4 | Low |  |  |  |  | 320198 | LAB1-17 | 320198 | LAB1-17 | Jan. 27, 2022 17:03 | Feb. 03, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:11 | 0 | 0 | Jan. 30, 2022 13:19 LAB1-17 Defect does not exist in version 1.1
3654899 | 68514 | ATM Project | 10 | ATM_1-10 | 293418 | Bug | 92944 | Exploratory | 64063 | 1.0 | OFF Button is not working | Function Being Tested: Checking the system "OFF" button Initial State of the System: User logged in after card is inserted. Input: Selecting the "OFF" button Expected Output: The system should turn off Actual Output: The system doesn't respond to the OFF button. | 3 | Resolved | 4 | Low |  |  |  |  | 320201 | KARTHIK KUMAR REDDY GANGIREDDY | 320198 | LAB1-17 | Jan. 27, 2022 17:10 | Feb. 03, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:20 | 0 | 0 | Jan. 30, 2022 13:20 LAB1-17 Defect does not exist in version 1.1
3654906 | 68514 | ATM Project | 11 | ATM_1-11 | 293418 | Bug | 92944 | Exploratory | 64063 | 1.0 | System not responding to keyboard functionalites. | Function Being Tested: keyboard functionality of quit(Ctrl+Q). Initial State of the System: User logged in after card is inserted. Input: Ctrl+Q Expected Output: The application should be closed. Actual Output: Ctrl+Q has no response. | 3 | Resolved | 4 | Low |  |  |  |  | 320199 | SATYA RELLU | 320198 | LAB1-17 | Jan. 27, 2022 17:18 | Feb. 03, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:11 | 0 | 0 | Jan. 30, 2022 13:21 LAB1-17 Defect does not exist in version 1.1
3657587 | 68514 | ATM Project | 12 | ATM_1-12 | 293418 | Bug | 92944 | Exploratory | 64063 | 1.0 | System doesnot display available account type for balance inquiry of card numbered 1 | Function Being Tested: Checking the balance of available accounts. Initial State of the System: System asks the customer to choose the account type. Input: Choosing the account type. Expected Output: Displaying available accounts in card numbered 1 are Checking & Savings Actual Output: Displaying Checking & Money Market account types. | 3 | Resolved | 3 | Normal |  |  |  |  | 320199 | SATYA RELLU | 320198 | LAB1-17 | Jan. 28, 2022 19:40 | Feb. 03, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:12 | 0 | 0 | Jan. 30, 2022 13:23 LAB1-17 Defect does not exist in version 1.1
3657594 | 68514 | ATM Project | 13 | ATM_1-13 | 293418 | Bug | 92944 | Exploratory | 64063 | 1.0 | System displays "invalid account type" for balance inquiry of card numbered 2 | Function Being Tested: Checking the balance of available accounts. Initial State of the System: System asks the customer to choose the account type. Input: Choosing the Money Market account type. Expected Output: System should generate receipt showing the available balance for Money Market account. Actual Output: System displays invalid account type. | 3 | Resolved | 3 | Normal |  |  |  |  | 320199 | SATYA RELLU | 320198 | LAB1-17 | Jan. 28, 2022 19:49 | Feb. 02, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:12 | 0 | 0 | Jan. 30, 2022 13:23 LAB1-17 Defect does not exist in version 1.1
3657598 | 68514 | ATM Project | 14 | ATM_1-14 | 293418 | Bug | 92944 | Exploratory | 64063 | 1.0 | System generating a receipt with incorrect transfer details. | Function Being Tested: To check the details of tranfer transaction in the generated receipt. Initial State of the System: To choose the accounts to transfer "from" and "to". Input: Choosing the account types. Expected Output: System should generate a receipt with correct details of the transaction. Actual Output: System generates a receipt with incorrect transaction detail. ( i.e. shows the amount transfered between the selected accounts in reverse order) | 2 | In Progress | 3 | Normal |  |  |  |  | 320201 | KARTHIK KUMAR REDDY GANGIREDDY | 320198 | LAB1-17 | Jan. 28, 2022 20:02 | Feb. 02, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:12 | 0 | 0 | Jan. 30, 2022 13:24 LAB1-17 Defect still exists in version 1.1
3657611 | 68514 | ATM Project | 15 | ATM_1-15 | 293418 | Bug | 92944 | Exploratory | 64063 | 1.0 | System generating receipt with incorrect deposit details. | Function Being Tested :Testing the system for legitimate deposit transaction details. Initial State of the System :System requests the customer to insert a envelope. Input :Customer inserting the envolope. Expected Output :System accepts the envelope and deposits the correct amount into the account selected. The receipt gets printed by the system with the correct updated balance details. Actual Output : System accepts the envelope and deposits the incorrect amount of cash into the selected account and generates the receipt with incorrect balance details. | 2 | In Progress | 3 | Normal |  |  |  |  | 320199 | SATYA RELLU | 320198 | LAB1-17 | Jan. 28, 2022 20:24 |  | 320198 | LAB1-17 | Feb. 03, 2022 11:21 | 0 | 0 | Jan. 30, 2022 13:25 LAB1-17 Defect still exists in version 1.1
3657613 | 68514 | ATM Project | 16 | ATM_1-16 | 293418 | Bug | 92944 | Exploratory | 64063 | 1.0 | Key board functionality does not work after selecting "CLEAR" button. | Function Being Tested: Checking the functionality of "CLEAR" button Initial State of the System: Input is given to the system. Input: Selecting the "CLEAR" button Expected Output: After selecting the CLEAR button, key board functionality should work. Actual Output: Key board functionality frozes. | 2 | In Progress | 3 | Normal |  |  |  |  | 320201 | KARTHIK KUMAR REDDY GANGIREDDY | 320198 | LAB1-17 | Jan. 28, 2022 20:39 | Feb. 02, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:13 | 0 | 0 | Jan. 30, 2022 13:26 LAB1-17 Defect still exists in version 1.1
3658544 | 68514 | ATM Project | 17 | ATM_1-17 | 293418 | Bug | 92944 | Exploratory | 64063 | 1.0 | Some system functionality works even after it is turned off. | Function Being Tested: Checking the system functionality after it is turned "OFF". Initial State of the System: User logged in after card is inserted. Input: Selecting the "OFF" button Expected Output: System should turn off and no functionality of the system should work. Actual Output: System turns off, but some functionalities like "take receipt" and "clear log" options works. | 2 | In Progress | 3 | Normal |  |  |  |  | 320200 | Chandrahas Reddy Pola | 320198 | LAB1-17 | Jan. 30, 2022 11:22 | Feb. 03, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:13 | 0 | 0 | Jan. 30, 2022 13:28 LAB1-17 Defect still exists in version 1.1
3658550 | 68514 | ATM Project | 18 | ATM_1-18 | 293418 | Bug | 92944 | Exploratory | 64063 | 1.0 | Systems ability to perform is effected when an incorrect input is given. | Function Being Tested: Checking the systems performance after a incorrect input is given. Initial State of the System: User logged in after card is inserted. Input: Random incorrect input is given to the system. Expected Output: Systems performance should not be effected. Actual Output: Systems performance slows down for a while until a correct input is given. | 3 | Resolved | 3 | Normal |  |  |  |  | 320201 | KARTHIK KUMAR REDDY GANGIREDDY | 320198 | LAB1-17 | Jan. 30, 2022 12:14 | Feb. 03, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:13 | 0 | 0 | Jan. 30, 2022 13:30 LAB1-17 Defect does not exist in version 1.1
3658559 | 68514 | ATM Project | 19 | ATM_1-19 | 293418 | Bug | 92944 | Exploratory | 64063 | 1.0 | Gramatical error | Function Being Tested: Spell checker. Initial State of the System: Asking for another transaction. Input: Selecting an option for transaction. Expected Output: System should display "Would you like to do another transaction?" . Actual Output: System displays "Wood you like to do another transaction?" . | 3 | Resolved | 4 | Low |  |  |  |  | 320200 | Chandrahas Reddy Pola | 320198 | LAB1-17 | Jan. 30, 2022 13:48 | Feb. 02, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:14 | 0 | 0 | Jan. 30, 2022 13:49 LAB1-17 Defect does not exist in version 1.1
3658591 | 68514 | ATM Project | 20 | ATM_1-20 | 293418 | Bug | 92944 | Exploratory | 64063 | 1.0 | System displays the incorrect transaction details in the log. | Function Being Tested: Deposit transaction details in the log. Initial State of the System: Deposit transaction is done . Input: Selecting the "Show logs" button. Expected Output: Displaying the correct deposit transaction details in the log. Actual Output: System displays incorrect deposit transaction details in the log. | 3 | Resolved | 3 | Normal |  |  |  |  | 320200 | Chandrahas Reddy Pola | 320198 | LAB1-17 | Jan. 30, 2022 15:46 | Feb. 02, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:14 | 0 | 0 | Jan. 30, 2022 15:46 LAB1-17 Defect does not exist in version 1.1
3658593 | 68514 | ATM Project | 21 | ATM_1-21 | 293418 | Bug | 92944 | Exploratory | 64063 | 1.0 | Record of incorrect numbered transactions in the log. | Function Being Tested: Record of transaction numbers in the log. Initial State of the System: System performing the transaction. Input: Selecting the "Show Log" button. Expected Output: Record of Transaction numbers in the log should be in correct order. Actual Output: System displays record of transaction numbers in the log in incorrect order. | 2 | In Progress | 3 | Normal |  |  |  |  | 320199 | SATYA RELLU | 320198 | LAB1-17 | Jan. 30, 2022 15:51 | Feb. 02, 2022 | 320198 | LAB1-17 | Feb. 03, 2022 11:15 | 0 | 0 | Jan. 30, 2022 15:51 LAB1-17 Defect does not exist in version 1.1